## Gantchart
GANTT CHART TEMPLATE					Smartsheet Tip ➜					A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.

PROJECT TITLE		Movie Recommendation System					COMPANY NAME					[Company's name]
PROJECT GUIDE		Prof. Sukhada Aloni					DATE					12/3/18

WBS NUMBER	TASK TITLE	TASK OWNER	START DATE	DUE DATE	DURATION(Weeks)	PCT OF TASK COMPLETE	PHASE ONE					PHASE TWO					PHASE THREE					PHASE FOUR
				WEEK 1					WEEK 2					WEEK 3					WEEK 4					WEEK 5					WEEK 6					WEEK 7					WEEK 8					WEEK 9					WEEK 10					WEEK 11					WEEK 12
				M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F
1	Project Conception and Initiation
1.1	Research paper search	Suraj Shetty	10/7/19	20/7/19	2	100%
1.1.1	Research paper finalization	Suraj,AkshayUdeg,Akshay Rathod	10/7/19	20/7/19	2	100%
1.2	Project Title	Suraj,AkshayUdeg,Akshay Rathod	10/7/19	20/7/19	2	100%
1.3	Abstract	Akshay Rathod	23/8/19	30/8/19	1	100%
1.4	Objectives	Suraj,AkshayUdeg,Akshay Rathod	23/8/19	30/8/19	1	100%
1.5	Literature Review	Suraj,AkshayUdeg,Akshay Rathod	23/8/19	30/8/19	1	100%
1.6	Problem Definition	Suraj Shetty	23/3/18	30/8/19	1	100%
1.7	Scope	Suraj Shetty	23/8/19	30/8/19	1	100%
1.8	Technology stack	Suraj,AkshayUdeg,Akshay Rathod	23/8/19	30/8/19	1	80%
1.9	Benefits for environment	Suraj,AkshayUdeg,Akshay Rathod	23/8/19	30/8/19	1	100%
1.1	Benefits for society	Suraj Shetty	23/8/19	30/8/19	1	100%
1.11	Applications	Akshay Rathod,Akshay Udeg	23/8/19	30/8/19	1	100%
2	Project Design
2.1	Proposed System	Suraj,AkshayUdeg,Akshay Rathod	19/9/19	27/9/19	1	100%
2.2	Design(Flow Of Modules)	Akshay Rathod	19/9/19	27/9/19	1	100%
2.3	Activity Diagram	Akshay Udeg	19/9/19	27/9/19	1	100%
2.4	Use Case Diagram	Suraj Shetty	19/9/19	27/9/19	1	100%
2.5	Description Of Use Case	Suraj,AkshayUdeg,Akshay Rathod	19/9/19	27/9/19	1	100%
2.6	Modules		19/9/19	27/9/19	1
2.6.1	Module-1	Suraj Shetty,Akshay Udeg,Akshay Rathod	27/9/19	24/10/19	3	80%
2.6.2	Module-2	Suraj Shetty,Akshay Udeg,Akshay Rathod	26/10/19	18/1/20	3
2.6.3	Module-3	Suraj Shetty,Akshay Udeg,Akshay Rathod	20/1/20	16/2/20	3

2.7	Preparation Of Report		19/9/19	27/9/19	1
3	Project Implementation
3.1	Module-1	Suraj Shetty,Akshay Udeg,Akshay Rathod	27/9/19	24/10/19	3	80%
3.2	Module-2	Y			0	0%
3.3	Module-3	Y			0	0%
3.4	Module-4	Z			0	0%
4	Testing
4.1	Design of Test Cases	Y			0	0%
4.2	Testing	Y			0	0%
5	Results and Analysis
5.1	Analysis Of Results	Y			0	0%
5.2	Graphical Representation	Y			0	0%
5.3	Report Preparation